## Sheet1
Primus Bank Defect/Bug Report Template
Defect | Defect Summary | Defect Description | Reproducable | Reproducable Steps | Defect Severity | Defect Priority | Defect Status | Detected By | Detected Date | Detected in Version | Assigned To | Fixed Date | Date Of Closure | Testcase Ref.
Defect 1 | Admin Change Password is not working | When we Click change Password in Admin Module,Instead of Dispalying Change Password Page,System displaying Run Time Error | Y | Step 1 : Launch Primusbank App Step 2 : Login As Admin Step 3 : Click change Password | High |  | New | Shubham Kongre |  | Build#1 |  |  |  | TC003
Defect 2 | Employee not able to login with new Password | When I change the password in employee module with giving valid old password,new password and confirm new password field and click submit System showing password has been change successfully but when I login with new password system showing incorrect Password/username | Y | Step 1 : Launch Primusbank Step 2 : Login As Employee Step 3 : Click change Password Step 4: Enter Old password,New Password and Confirm New Password and Submit Step 5: Logout Step 6:Login with new Password | Very High |  | New | Shubham Kongre |  | Build#1 |  |  |  | TC006
Defect 3 | System showing Branch Created Successfully with Unmandatory field | When I Enter some data in Unmandatory fields and click Submit for new Branch Creation then Instead of Showing Error Message Mandatory Field Required System shows Branch Created Successfully | Y | Step 1:Launch primus Bank Step 2:Login as Admin Step 3:Click on Branches and then New Branches Step 4:Enter Some data in Unmandatory field like Address 2,Address 3 and Area and Click Submit | High |  | New | Shubham Kongre |  | Build#2 |  |  |  | TC008
Defect 4 | System showing Branch Created Successfully while leaving mandatory and unmandatory field blank | When I Leave all the Unmandatory and mandatory field blank and Click Submit instead of Showing Error Message Mandatory Field required System Showing Branch Created successfully | Y | Step 1:Launch primus Bank Step 2:Login as Admin Step 3:Click on Branches and then New Branches Step 4:Leave all the Field mandatory and Unmandatory Blank and click Submit | High |  | New | Shubham Kongre |  | Build#2 |  |  |  | TC009
Defect 5 | System Shows new Role already exist with unmandatory field and leaving mandatory and unmandatory filed blank | When I leave all the Unmandatory and mandatory field blank and Click Submit instead of Showing Error Message Mandatory Field required System Showing New Role already Exist and also when I enter valid Data in only mandatory field and click submit Instead of showing error message Mandatory field Required System shows New Role Already exist | Y | Step 1:Launch primus Bank Step 2:Login as Admin Step 3:Select Roles and click on new Roles Step 4:Enter Valid Data in UnMandatory field and click Submit Step 5:Leave Mandatory Field and Unmandatory field blank and click Submit | High |  | New | Shubham Kongre |  | Build#3 |  |  |  | TC0011 and TC0012
Defect 6 | System shows New Employee Created Successsfully while Leaving all The Mandatory field blank | When I leave all the Mandatory field Blank Instead Of Showing Error Message Mandatory Field Required System Shows New Employee Created Successfully | Y | Step 1:Launch Primus Bank Step 2:Login As Admin Step 3:Select on Employee and click on New Employee Step 4:Leave all Mandatory field blank and Click Submit | High |  | New | Shubham Kongre |  | Build#4 |  |  |  | TC0014